# Project Status

System for AIIMS Human Resource and Account Services (SAHAS 2.0)

AIIMS, New Delhi

1st-May-2026 to 31st-May-2026

Centre for Development of Advanced Computing

(A Scientific Society of the Ministry of Communications and Information Technology, Govt. of India)

NOIDA Unit

C-56/1, Institutional Area, Sector-62, Noida-201307

Phone: 91-120-3063311 - 13 Fax: 91-120-3063317

Website: www.cdacnoida.in

- Project details

- Project Name: SAHAS 2.0, AIIMS Delhi

- Location: AIIMS Delhi

- Project Methodology: Agile

- Project Start Date: 1st January 2026

- Period: 01st  May 2026 to 31st May 2026

- Milestone achieved

- New Feature Integration: The new Item master for maker and checker has been completed.

- Adhoc Data: The requested Fund/Re-fund booking and expenditure data, along with the pendency details, has been provided to AIIMS for 2025-26 and 2026-27.

- On-boarding of recruitment cell: The recruitment cell has been trained regarding how to register employees on SAHAS for all the caders.

- Leave Financial Impact: The Leave Module has been live for PAN AIIMS since 15th April 2026. Leaves that have a financial impact on employees’ salaries are now being processed accordingly, and salary deductions are being applied where applicable.

- Implementation of New UI for Reports, Masters & Services: Several modules under Reports, Masters and Services have been upgraded with a new UI design to improve usability and clarity. The updated interface provides better layout structuring, improved navigation, and enhanced readability of data

- Arrear Approval Report: The New Arrear Approval Report has been provided in the View section of the Forward/Freezed Demand screen in Arrear Approval. Enables users to view the report of Freezed demand directly from this section.

- GPF Module refinement and new features updation:

  - G P F Withdrawal Request - Emp

  - G P F Withdrawal Request - Admin

  - G P F Application Tracking

  - G P F Withdrawal - Clerk

  - G P F Withdrawal Common Approval

Above features successfully tested on UAT and now available for users in production.

- NTP (Not to Pay) Feature: The Not to Pay (NTP) functionality has deployed on the production environment for User usability.

- APAR Module: The APAR module has been running successfully well over two years and currently the total APAR’s generated are 14,253 by the establishment for the current reporting year 2025–2026.

| Status | Total |
| --- | --- |
| Draft/Initiated | 15 |
| In Process | 11,956 |
| Complete | 871 |
| NRC | 1404 |
| On Deputation | 7 |
| Total | 14,253 |

- APAR Representation: 234 APAR have been represented for the Reporting Year 2025-2026 till now.

- APAR date cutoff: APAR cutoff date has been extended two times (15th May & 15th June) in May 2026.

- IGOT Course details: The requested change to add the IGOT course details option in the APAR template has been implemented and is working properly on the production server.

- AIPR: The AIPR module is successfully run in the AIIMS for the 2nd consecutive year 2025 with highest ever digital fillings so far.

| Declaration Status | Count |
| --- | --- |
| New | 75 |
| Rejected By Vigilance | 47 |
| Submitted To Vigilance | 9279 |
| Accepted By Vigilance | 20 |
| Total | 9421 |

- Pension Module: The Pension Cell and they have processed 41 pension files through the Pension module in SAHAS.

- Training Session: Multiple training sessions, including hands-on sessions, on the Pension Module and Leave Module were conducted for dealing users, Establishment users, and the Pension team.

- Two sessions were conducted of the Leave Module on dated 7th & 18th May 2026 for 46 Employees.

- In May 2026 around 13-employees were trained on TADA & LTC modules in one-session.

- One session was conducted for the Dynamic work/supply order on 19th May 2026.

- Leave Module: Current Leave status across PAN AIIMS New Delhi.

| Filled Leave Status |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Draft | New | In-process | Approved | Revert Back | Rejected | Cancelled | Cancellation in progress | Partial Cancel | LTC Hold | Total |
| 114 | 424 | 1103 | 7975 | 375 | 274 | 214 | 82 | 0 | 23 | 10584 |

- SAHAS 2.0: New Work Order SAHAS 2.0 has been given to CDAC including following modules.

| SCHEDULE 1 |  |  | SCHEDULE 2 |  |  |
| --- | --- | --- | --- | --- | --- |
| S. No. | Modules | Status | S. No. | Module | Status |
| 1 | AIPR | Rolled out in 2025 | 6 | Rate of Contract | In Second Schedule |
| 2 | Cheque Generation | Rolled out in 2025 | 7 | Impreset | In Second Schedule |
| 3 | Vacation | Design Document finalization required from AIIMS Concern Authority | 8 | Vigilance | In Second Schedule |
| 4 | Payment Retrieval Module | Module under development | 9 | No dues | In Second Schedule |
| 5 | Exam | Design Document is under process | 10 | Finance Concurrence | In Second Schedule |

- Change Requests and Problem Reports: Status for the month of May’2026.

| Created Tracker counts in April'26 |  |  |  | Closed Tracker counts in April'26 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Trackers | HRMS | FMS | Paybill | Trackers | HRMS | FMS | Pay bill |
| CR | 9 | 2 | 3 | CR | 2 | 0 | 0 |
| PRS | 1 | 1 | 0 | PRS | 0 | 0 | 0 |
| Activity | 19 | 1 | 9 | Activity | 15 | 0 | 9 |
| Total: | 29 | 4 | 12 | Total: | 17 | 0 | 9 |

- Help Desk: A Help Desk email (sahas@aiims.edu) has been set up as another touch point to address user issues formally Usually TAT for addressing issues is within one working day.

SAHAS Helpdesk Summary

| TICKET STATUS MAY'2026 |  |  |
| --- | --- | --- |
| TICKET STATUS | TICKET COUNT | IN % |
| Closed | 113 | 82% |
| In Process | 2 | 1% |
| Open | 23 | 17% |
| Grand Total | 138 | 100% |

| TICKET STATUS YTD'2026-2027 |  |  |
| --- | --- | --- |
| TICKET STATUS | TICKET COUNT | IN % |
| Closed | 379 | 88% |
| In process | 8 | 2% |
| Open | 43 | 10% |
| Grand Total | 430 | 100% |

- Milestone under Execution

- 24Q and Monthly Tax OR Match: The team is working on matching the Monthly TAX OR and the 24Q Report, center wise to minimize the sort deduction and income tax issue.

- TADA Module: Required changes have been provided to the development team; implementation is in progress.

- Exam module: The Exam Cell Module design-PRD (Product Requirement Document) is deemed approved and shared with the Development team for further development.

- Date of Delivery: Further improvement has been shared with the development team for auto calculation of days. Scope document and design document have been approved and shared.

- Deduction Bank Mapping Master: Deduction Bank Mapping Master: Changes related to budget-wise mapping for voucher bills and Centre-wise mapping for PAYBILL employee bills have been received from stakeholders and AOIT, shared with the development team, and are currently in progress.

- Work Order-Dynamic: The new dynamic work order/approval process for the store section will be implemented after completion of the store account mapping master.

- PFMS API Integration: PFMS Integration between CDAC and CAG team is still ongoing.

- Assets/Expenditure Register Report: Given report format has been provided to the dev team.

- Ledger Master: The new enhancements in the ledger master, including the valid/invalid functionality, have been completed in the UAT environment.

- Bill Processing-Dynamic: The work is in progress based on the observations shared by the PMU following the demonstration.

- Fund/Re-fund Booking Report: Work on the new functionality is currently in progress, as requested by the budget section.

- Dynamic User Mapping Master: The design provided by the PMU has been shared with the development team.

- PURCHASE REPORT: Report has been completed in the UAT environment for the CGA team.

- Dashboard (FMS): Dashboard is currently in progress, as requested by Sr. FA.

- Promotion and Transfer & Posting Module: As a directive from the PMU Head, the Promotion and Transfer & Posting modules will be initiated in the Recruitment Cell.

- Next Milestone

- Payment Retrieval Module: Under development. Scope document and design document have been prepared and shared.

- Vacation Module Design Document Finalization: Design document has been finalized and now it is under development.

- Exam Module: Design document has been finalized and now it is under development.

- Study on Rate Contract Module: A study on the Rate Contract module is ongoing to determine its scope for future projects.

- Deductions Voucher: The new voucher will be generated from FMS regarding all deductions (FMS, Paybill).

- Bill Details Report: The new bill details report for cheque and PFMS payments will be provided to AIIMS.

- Step-Up and HR Event Revert: Currently the back-end team is contemplating the appropriate solutions to improvise step-up and all other revert provision in HR events such as Increment, MACP, Promotion and Employment status etc.

- Optimization of Bill Reimbursement Process: The Bill Reimbursement process is being refined to make it more efficient and user-friendly. This includes simplifying submission workflows, improving validation mechanisms, and ensuring faster approval and processing cycles.

- Points needing attention

- AIIMS CAPFIMS: The CAPFIMS Work order due for issuance by concerned authority.

- Prioritize change requests to ensure timely development for the SAHAS and SAHAS 2.0 both work orders.

- Employee Bill Reimbursement: AIIMS have to circulate Office Order to roll out Employee Bill Reimbursement process on production environment.

- News Paper Reimbursement.

- Learning Resource Allowance

- Children Education Allowance

- Leave Travel Allowance

- Office Bag Reimbursement

- TADA

- The Store Department needs Master Trainers.

- FD user needs to complete payment cycle -Up to dispatch process within the SAHAS to avoid any discrepancy in Fund booking Carry forward.

- NTP (Not to Pay) Feature: A meeting has been requested by AO eHRMS with AO IT and PMU team before the Roll out on the production server.

- Recruitment Cell On-boarded: The Recruitment Cell on-boarded is due for a long time for the "Transfer & Posting" and "Promotion" modules in SAHAS.

- GPF – Employee-Specific Withdrawal Request: A new process has been added in the SAHAS Application so employees can request GPF withdrawals by themselves. To familiarize all concerned users with this feature, a demo/training session needs to be scheduled.

- Role Management: Currently we are seeking clarification from PMU/AIIMS Establishment on the Role Management design.

- Modules to go live: As per the work order schedule, the Transfer & Posting, and Grievance modules have been demonstrated and are now awaiting official roll-out orders from the concerned authority.

- GAD Approval: The finalized GAP Analysis Document (GAD) for Schedules 1, 2, and 3 has been pending approval for a long time and the follow-up is on with PMU.

- Team is waiting for response regarding pendency of Employee Acceptance mail to concern Account officer and AO IT.

- CDAC has completed API Integration for the ESD for bill processing and payment through SAHAS. And currently the prebilling process is under development by the CEL and Tender wizard.

- Compilation: Kindly issue an order directing all centers to make payments bill-wise for deductions related to voucher and salary bills, so that we complete the dashboard for upper management.

- HR Changes Priority: Team is still waiting for the priority decision of HR Module changes which have been received from several Establishments.

-------------------------------------------------------------END OF REPORT-----------------------------------------------------------------